## Test Report
TEST REPORT
Project Name | Summer Cultivation Course Management System for Co Loan Pagoda |  | ThuyDTT
Project Code | SCCMS |  | ĐĐ Thích Thanh Dân
Document Code | SCCMS_TestReport5.4_v1.0 |  | 2024-12-04
Notes
No | Yes | No | N/A | Number of test cases
1 | 45 | 0 | 0 | 45
Summary | 45 | 0 | 0 | 45
| Test coverage | 100%
| Test successful coverage | 100%

## Acceptance Test
Acceptance Test
Project Name | Summer Cultivation Course Management System for Co Loan Pagoda |  | Creator | ThuyDTT
Project Code | SCCMS |  | Reviewer/Approver | ĐĐ Thích Thanh Dân
Document Code | SCCMS_TestReport5.4_v1.0 |  | Issue Date | 2024-12-04
Notes
ID | Checklist |  |  |  | Test Result
[5 empty] | Pass | Fail
GUI and Usability
1 | The website design takes inspiration from the following design: Figma Design |  |  |  | TRUE | FALSE
2 | The screen is well-organized, providing a user-friendly interface. |  |  |  | TRUE | FALSE
3 | The steps are short and easy to understand so that the user can interact with the application without training |  |  |  | TRUE | FALSE
4 | The main functions are organized into tabs, facilitating easier access and navigation for users. |  |  |  | TRUE | FALSE
5 | Links, buttons, and checkboxes are easily clickable. |  |  |  | TRUE | FALSE
6 | Important commands are displayed as buttons with distinct background colors. |  |  |  | TRUE | FALSE
7 | The displayed text is in Vietnamese for the convenience of most users |  |  |  | TRUE | FALSE
8 | The static text is clear, concise, and meaningful. |  |  |  | TRUE | FALSE
9 | Pop-up menus are provided for the user to access information about an object's properties or perform specific tasks on the object. |  |  |  | TRUE | FALSE
10 | System display notification message when meet trouble, error. |  |  |  | TRUE | FALSE
Security
11 | The system must use token-based authentication, in which the authentication server returns an access token user logged in |  |  |  | TRUE | FALSE
Performance
12 | All web pages shall load completely within 5 seconds over a standard broadband connection (10 Mbps) under normal load conditions. The system shall retrieve and display requested data (e.g., course lists, user profiles) within 4 seconds after a query is submitted. |  |  |  | TRUE | FALSE
Feature
| Function | Test case description | Test Case Proceduce | Expected Result | Pass | Fail
13 | Login | Users can login with username and password with authorized account | 1. Access to SCCMS via link 2. Navigate to Login screen 3. Login with authorized account | 1. Display login page 2. Navigate to homepage of authorized account 3. If the password and username is invalid or incorrect, the system will display an error message. | TRUE | FALSE
14 | Import user list | Users can create multiple accounts by importing a user list file. | 1. Login with manager account 2. Click on 'Danh sách người dùng' in 'Người dùng' on navbar 3. Click on 'Nhập từ tệp' button 5. Click on 'Chọn tệp' button 6. Choose file 7. Click on 'Xác nhận' button | 1. SCCMS will display success message 2. Navigate to user list screen 3. Send account information via email to users 4. If the input fields are invalid, the system will report an error and cannot create successfully. | TRUE | FALSE
15 | Create course | Users login with manager account and create course | 1. Login with manager account 2. Click on 'Khóa tu' on navbar 3. Click on 'Tạo mới' button 5. Input following data: 'Tên khóa tu': 'Khóa tu mùa hè 2025' 'Thời gian bắt đầu khóa tu' :05/01/2025 'Thời gian kết thúc khóa tu': 05/30/2025 'Thời gian đăng ký khóa sinh': 04/01/2025 In 'Thời gian đăng ký khóa sinh': 04/30/2025 'Thời gian đăng ký tình nguyện viên': 04/01/2025 In 'Thời gian đăng ký tình nguyện viên':04/30/2025 'Số lượng khóa sinh dự kiến': 100 'Mô tả': 'Khóa tu dành cho học sinh năm 2025 ' 6. Click on 'Tạo khóa tu' button | 1. SCCMS displays successfull message. 2. SCCMS redirects to "Danh sách khóa tu" screen. 3.The course selection dropdowns on other screens will have the newly added course added. 4. If the input fields are invalid, the system will report an error and cannot create successfully. | TRUE | FALSE
16 | Create student group | Users login with manager account and create student group in a course | 1. Login with manager account 2. Click on 'Chánh' on navbar 3. Choose course 4. Click on 'Thêm chánh' button 5. Enter student group name: "Đạo" 6. Select gender: Nữ 7. Seclect supervisor: thuylh 8. Click on 'Tạo chánh' button | 1. Display success message: 'Tạo thành công' 2. SCCMS redirects to student group list screen 3.The student group selection dropdowns on other screens will have the newly added student group added. 4. If the input fields are invalid, the system will report an error and cannot create successfully. | TRUE | FALSE
17 | Create team | Users login with manager account and create team in a course | 1. Login with available account 2. Click on 'Ban' on navbar 3. Choose course: 'Khóa tu mùa thu 2024' 4. Click on 'Thêm ban' button 5. Enter team name: "Ban tri khách 2" 6. Select gender: 'Tất cả' 7. Expected quantity: 10 8. Seclect leader: 'quyenht' 9. Click on 'Tạo ban' button | 1. Display success message: 'Tạo ban thành công' 2. SCCMS redirects to team list screen 3.The team selection dropdowns on other screens will have the newly added team added. 4. If the input fields are invalid, the system will report an error and cannot create successfully. | TRUE | FALSE
18 | Add post | Users can login with manager account and create post | 1. Login with manager account 2. Click on 'Bài đăng' on navbar 3. Click on 'Thêm mới' button 4. Choose file in 'ảnh cover' 5. Select type of post: 'Hoạt động' 6. Input 'Tiêu đề': 'Thượng tọa Thích Minh Quang đắc cử trưởng ban trị sự phật giáo tỉnh' 7. Input 'Nội dung': 'Sáng ngày 09 tháng 06 năm 2022, tại hội trường khách xá chùa Bái Đính (huyện Gia Viễn, tỉnh Ninh Bình) đã diễn ra Đại hội đại biểu Phật giáo tỉnh lần thứ VII (nhiệm kỳ 2022 – 2027), dưới sự chứng minh tối cao của Trưởng lão Hòa thượng Thích Trí Quảng – Quyền Pháp chủ GHPGVN. Ngoài ra còn có sự chứng minh của nhị vị Hoà thượng Thành viên HĐCM: Hoà thượng Thạch Huôn, Hoà thượng Lý Sa Mouth; Hòa thượng Thích Thiện Nhơn – Chủ tịch HĐTS GHPGVN; nhị vị Hòa thượng Phó chủ tịch thường trực HĐTS GHPGVN: Hòa thượng Thích Thiện Pháp, Hòa thượng Thích Thanh Nhiễu; chư Tôn đức Phó chủ tịch HĐTS GHPGVN: Hòa thượng Thích Gia Quang, Hoà thượng Thích Quảng Tùng; Hoà thượng Yoshimizu Daichi – Nguyên Hội trưởng Hội Tịnh Độ Tông Nhật Bản… cùng chư tôn đức HĐTS GHPGVN.' 8. Click on 'Tạo bài đăng' button | 1. Display success message: 'Tạo thành công' 2. SCCMS redirects to post list screen 3. The status of the post will be set to 'Bản nháp' 4. If the status is changed to 'Show', the post will appear on the home page 5. If the input fields are invalid, the system will report an error and cannot create successfully | TRUE | FALSE
19 | Submit student application for a course | Parents can submit applications for their children on the SCCMS system. | 1. Parent accesses to SCCMS via link. 2. Click on 'Đăng ký khóa sinh' in 'Đăng ký' on navbar 3. Select 'Chào mừng tết 2025' in 'Khóa tu' drop list 4. Enter input in 'Họ và Tên': 'Đỗ Thị Thanh Thủy' 5. Enter input in 'Số CMND/CCCD': 001302037123 6. Select in 'Giới tính': Nữ 7. Select date of birth: 12/02/2008 8. Enter input in 'Học lực': 'Giỏi' 9. Enter input in 'Hạnh kiểm': 'Tốt' 10. Enter input in 'Địa chỉ': 'Hòa Lạc' 11. Enter input in 'Họ tên cha/mẹ': 'Nguyễn Dung' 12. Enter input in 'Số điện thoại cha/mẹ': '0973506887' 13. Enter input in 'Email': 'thuydtt1903@gmail.com' 14. Choose image file in 'Ảnh thẻ' 15. Choose image file in CCCD 'Mặt Trước' 16. Choose image file in CCCD 'Mặt Sau' 17. Click on capcha 'I'm not a robot' 18. Click on 'Đăng ký' button | 1. SCCMS displays successfull message. 2. SCCMS redirects to successfull registration page 3. If the input fields are invalid, the system will report an error and cannot create successfully. | TRUE | FALSE
20 | Auto-assign student applications for secretaries | Manager can auto assign applications to secretaries | 1. Login with account available. 2. Click on 'Đơn đăng ký khóa sinh' in 'Đơn đăng ký' on navbar. 3. Choose course 3. Click on 'Chia thư ký' button | 1. SCCMS displays successfull message. 2. All applications will be divided equally among the secretaries. 3.Applications that have been assigned to a certain secretary will remain with that secretary. 4. Secretaries recive notifications 5. If all applications have been processed, a message will be displayed: 'Không có đơn để chia' 6. If there is no secretary to divide, the system will report an error: 'Không có thư ký nào để chia' | TRUE | FALSE
21 | Accept/Reject applications | User can login with manager account or secretary account and accept or reject student application | 1. Login with manager or secretary account 2. Click on 'Đơn đăng ký' on navbar 3. Click choose a course 4. Click on eye icon button of student appliaction 5. Click on 'Từ chối' or 'Duyệt đơn' button | 1. SCCMS redirects to 'Chi tiết đơn đăng ký' screen 2. SCCMS displays successfull message. 3. Status will be changed 4. If the course has already started, the application can no longer be approved or rejected. 5. If the secretary is not the secretary assigned to that application, the system will not display the 'Duyệt đơn' and 'Từ chối' button. | TRUE | FALSE
22 | Auto-assign students to groups | Once all applications are processed, the secretary or manager can automatically assign students into student groups. | 1. Login with manager or secretary account 2. Click on 'Đơn đăng ký' on navbar 3. Click choose a course 4. Click on 'Phân chánh' button 5. Click on 'Xác nhận' button in confirm pop-up | 1. SCCMS displays successfull message. 2. SCCMS redirects to student application list screen 3. All students will be divided into student groups. 4. Students who were manually assigned to a previous student group will remain in their original group. 5. If the application has not been fully processed, the system will display an error message. | TRUE | FALSE
23 | Send bulk result emails to parents | After assigning students into student groups, the secretary or manager will send the results to the students' parents via email. | 1. Login with manager or secretary account 2. Click on 'Đơn đăng ký' on navbar 3. Click choose a course 4. Choose student application that want to send results 5. Click on 'Gửi kết quả' button 6. Select email template: 'Khóa sinh trúng tuyển' 7. Click on 'Gửi' button | 1. SCCMS displays successfull message. 2. SCCMS redirects to student application list screen 3. Send emails to parents 4. If the user do not select the application to send email, the system will display an error message. | TRUE | FALSE
24 | Auto-generate student cards | User can login with manager account or secretary account and generate student cards | 1. Login with manager or secretary account 2. Click on a course 3. Click on 'Khóa sinh' on navbar 4. Select the student you want to create a card 5. Click on 'In thẻ' button | 1. Display success message: 'Thành công' 2. SCCMS redirects to 'Khóa sinh' screen 3. Card file will be downloaded 4. If the user do not select the application to send email, the system will display an error message. | TRUE | FALSE
25 | Export student list | User can login with manager account or secretary account and export student list | 1. Login with available account 2. Click on a course 3. Click on 'Khóa sinh' on navbar 4. Click on 'Xuất excel' button | 1. Display success message: 'Tải file thành công' 2. SCCMS redirects to 'Khóa sinh' screen 3. Student list file will be downloaded | TRUE | FALSE
26 | Auto-assign supervisors to student groups | User can login with manager account or secretary account and auto assign supervisors into student groups | 1. Login with manager or secretary account 2. Click on 'Chánh' on navbar 3. Choose course: Khóa tu mùa thu 2024 4. Click on 'Phân huynh trưởng' button 5. Click on 'Xác nhận' button in confirm pop-up | 1. Display success message: 'Tự động phân chia thành công' 2. SCCMS redirects to student group list screen 3. Supervisors will be assigned into student groups. 4. Supervisors who were manually assigned to a previous student group will remain in their original group. 5. If there is no supervisor, the system will display an error message. | TRUE | FALSE
27 | Submit volunteer application for a course | Volunteers submit applications for themself on the SCCMS system. | 1. Volunteers accesses to SCCMS via link. 2. Click on 'Đăng ký tình nguyện viên' in 'Đăng ký' on navbar 3. Select 'Chào mừng Tết 2025' in 'Khóa tu' drop list 4. Enter input in 'Họ và Tên': 'Nguyen Duy Phuc' 5. Enter input in 'Số CMND/CCCD': 037203003511 6. Select in 'Giới tính': Nam 7. Select date of birth: 10/04/2003 8. Enter input in 'Địa chỉ': 'Phúc Nam, Phúc Thành, Thành phố Ninh Bình' 9. Enter input in 'Số điện thoại': '0911468929' 10. Enter input in 'Email': 'nguyenphuc.nb03@gmail.com' 11. Choose image file in 'Ảnh thẻ' 12. Choose image file in CCCD 'Mặt Trước' 13. Choose image file in CCCD 'Mặt Sau' 14. Click on capcha 'I'm not a robot' 15. Click on 'Đăng ký' button | 1. SCCMS displays successfull message. 2. SCCMS redirects to successfull registration page 3. If the input fields are invalid, the system will report an error and cannot create successfully. | TRUE | FALSE
28 | Auto-assign volunteer application for secretaries | Manager can auto assign applications to secretaries | 1. Login with account available. 2. Click on 'Đơn đăng ký tình nguyện viên' in 'Đơn đăng ký' on navbar. 3. Choose course 3. Click on 'Chia thư ký' button | 1. SCCMS displays successfull message. 2. All applications will be divided equally among the secretaries. 3.Applications that have been assigned to a certain secretary will remain with that secretary. 4. Secretaries recive notifications 5. If all applications have been processed, a message will be displayed: 'Không có đơn để chia' 6. If there is no secretary to divide, the system will report an error: 'Không có thư ký nào để chia' | TRUE | FALSE
29 | Accept/Reject volunteer applications | User can login with manager account or secretary account and accept or reject volunteer application | 1. Login with manager or secretary account 2. Click on 'Đơn đăng ký tình nguyện viên' in 'Đơn đăng ký' on navbar. 3. Click choose a course 4. Click on eye icon button of volunteer appliaction 5. Click on 'Từ chối' or 'Duyệt đơn' button | 1. SCCMS redirects to 'Chi tiết đơn đăng ký' screen 2. SCCMS displays successfull message. 2. Status will be changed 4. If the course has already started, the application can no longer be approved or rejected. 5. If the secretary is not the secretary assigned to that application, the system will not display the 'Duyệt đơn' and 'Từ chối' button. | TRUE | FALSE
30 | Auto assign volunteer to team | Once all applications are processed, the secretary or manager can automatically assign volunteers into teams | 1. Login with manager or secretary account 2. Click on 'Đơn đăng ký tình nguyện viên' in 'Đơn đăng ký' on navbar 3. Click on 'Phân ban' button 4. Click on 'Xác nhận' button in confirm pop-up | 1. SCCMS displays successfull message. 2. SCCMS redirects to volunteer application list screen 3. Volunteers will be divided into teams. 4. Volunteers who were manually assigned to a previous team will remain in their original team. 5. If the application has not been fully processed, the system will display an error message. | TRUE | FALSE
31 | Send results to volunteer via email | After assigning volunteers into teams, the secretary or manager will send the results to the volunteers via email. | 1. Login with manager or secretary account 2. Click on 'Đơn đăng ký' on navbar 3. Click choose a course 4. Choose student application that want to send results 5. Click on 'Gửi kết quả' button 6. Select email template: 'Tình nguyện viên trúng tuyển' 7. Click on 'Gửi' button | 1. SCCMS displays successfull message. 2. SCCMS redirects to volunteer application list screen 3. Send emails to volunteers. 4. If users don't choose volunteer to send email, system will display an error mesage | TRUE | FALSE
32 | Export volunteer list | User can login with manager account or secretary account and export volunteer list | 1. Login with available account 2. Click on a course 3. Click on 'Tình nguyện viên' on navbar 4. Click on 'Xuất excel' button | 1. SCCMS display success message: 'Tải file thành công' 2. SCCMS redirects to 'Danh sách tình nguyện viên' screen 3. Volunteers list file will be downloaded | TRUE | FALSE
33 | Generate volunteer cards | User can login with manager account or secretary account and generate volunteer cards | 1. Login with manager or secretary account 2. Click on a course 3. Click on 'Tình nguyện viên' on navbar 4. Select the volunteer you want to create a card 5. Click on 'In thẻ' button | 1. SCCMS display success message: 'Thành công' 2. SCCMS redirects to 'Tình nguyện viên' screen 3. Card file will be downloaded 4. If the user do not select the application to send email, the system will display an error message. | TRUE | FALSE
34 | Generate volunteer certificate | User can login with manager account or secretary account and generate volunteer certificates | 1. Login with manager or secretary account 2. Click on a course 3. Click on 'Tình nguyện viên' on navbar 4. Select the volunteer you want to create a card 5. Click on 'In chứng nhận' button | 1. SCCMS display success message: 'Thành công' 2. SCCMS redirects to 'Tình nguyện viên' screen 3. Certificate files will be downloaded 4. If the user do not select the application to send email, the system will display an error message. | TRUE | FALSE
35 | Create room | When the course be ongoing or upcoming manager can create new room. | 1. Login with manager account 2. Click on 'Trực đêm' on navbar 3. Click on 'Cấu hình' 4. Choose course 5. Click on 'Thêm mới' in 'Danh sách phòng' 6. Input room name: 'B1' 7. Select gender: 'Nam' 8. Select student group: 'Đạo' 9. Input quantity: 2 10. Click on 'Tạo phòng' button | 1. SCCMS display success message: 'Tạo thành công' 2. SCCMS redirects to night shift configuration screen 3. If the input fields are invalid, the system will report an error and cannot create successfully. | TRUE | FALSE
36 | Create shift | When the course be ongoing or upcoming manager can create new shift | 1. Login with manager account 2. Click on 'Trực đêm' on navbar 3. Click on 'Cấu hình' 4. Choose course: Khóa tu mùa thu 2024 5. Click on 'Thêm mới' in 'Danh sách ca trực' 6. Input Start Time: 8:00 PM 7. Input End Time: 10:00 PM 8. Click on 'Tạo' button | 1. SCCMS display success message: 'Tạo ca trực thành công' 2. SCCMS redirects to night shift configuration screen 3. If the input fields are invalid, the system will report an error and cannot create successfully. | TRUE | FALSE
37 | Edit shift registration time | The manager can edit night shift registration opening time | 1. Login with manager account 2. Click on 'Trực đêm' on navbar 3. Click on 'Cấu hình' 4. Choose course: Khóa tu mùa thu 2024 5. Choose time in 'Thời gian mở đơn' 6. Input Start Time: 22/11/2024 7. Input End Time: 30/11/2024 8. Click on 'Lưu thay đổi' button | 1. SCCMS display success message: 'Cập nhật thành công' 2. SCCMS redirects to night shift configuration screen 3. If the input fields are invalid, the system will report an error and cannot create successfully. | TRUE | FALSE
38 | Register free time | After the registration free time opens, staff can register for the days they are free to schedule night shifts. | 1. Login with staff account 2. Click on 'Trực đêm' on navbar 3. Click on 'Đăng ký ca trực' 4. Choose course: Khóa tu mùa thu 2024 5. Click on dates you are free 6. Click on 'Gửi' button | 1. SCCMS display success message: 'Cập nhật thành công' 2. SCCMS redirects to 'Đăng ký ngày trực' screen 3. Selected dates will be circled on the calendar. 4. If the registration time is over, the system will not display the calendar for staff to choose dates. | TRUE | FALSE
39 | Automatically assign night shifts | After staffs register their free time, manager can login automatically assign night shifts. | 1. Login with manager account 2. Click on 'Trực đêm' on navbar 3. Click on 'Danh sách ca trực' 4. Choose course: Khóa tu mùa thu 2024 5. Click on 'Chia nhân viên' button | 1. SCCMS display success mesage: 'Chia lịch thành công' 2. Navigate to 'Danh sách ca trực' screen 3. The staff who were previously manually assigned will remain the same | TRUE | FALSE
40 | View night shift list | Users can reject their assigned night shifts | 1. Login with available account 2. Click on 'Trực đêm' on navbar 3. Click on 'Lịch trực' | 1. Navigate to 'Lịch trực' screen 2. Assigned night shifts will be displayed. | TRUE | FALSE
41 | Reject a night shift | Users can reject their assigned night shifts | 1. Login with staff account 2. Click on 'Trực đêm' on navbar 3. Click on 'Lịch trực' 4. Click on night shift asignment 5. Click on 'Từ chối' button 4. Input 'Lý do': 'Tôi bận' 4. Click on 'Gửi' button | 1. SCCMS display success message: 'Từ chối ca trực thành công' 2. SCCMS redirects to 'Lịch trực' screen 3. Scretary will be recieve notification 4. In the 'Lịch trực' screen, the staff who has previously declined a shift will have the status 'Từ chối' displayed. 5. Rejection will be displayed in 'Danh sách hủy ca' screen | TRUE | FALSE
42 | Reassign staff for night shift | Users can reassign the night shift to someone else | 1. Login with manager account 2. Click on 'Trực đêm' on navbar 3. Click on 'Danh sách hủy ca' 4. Choose course 5. Click on 'Chi tiết' button 6. Choose staff 7. Click on 'Cập nhật' button | 1. SCCMS display success message: 'Cập nhật thành công' 2. SCCMS navigate to 'Danh sách ca trực bị từ chối và bị hủy' screen. 3. Staff assigned to the shift will receive notification. 4. In the 'Lịch trực' screen, the staff who has previously declined a shift will have the status 'Đã hủy' displayed. | TRUE | FALSE
43 | Submit night shift report | Staff can submit night shift report report | 1. Login with staff account 2. Click on 'Danh sách ca trực' 'Trực đêm' on navbar 3. Click on 'Chi tiết' button 4. Choose absent and present 5. Click on 'Nộp báo cáo' button | 1. SCCMS display success message: 'Nộp báo cáo thành công' 2. SCCMS navigate to 'Chi tiết báo cáo' screen 3. Status of report will be changed | TRUE | FALSE
44 | Submit daily report | Supervisors can submit daily report report | 1. Login with supervisor account 2. Click on 'Báo cáo' on navbar 3. Click on eye icon button of student group 4. Choose absent and present 5. Click on 'Nộp báo cáo' button | 1. SCCMS display success message: 'Nộp báo cáo thành công' 2. SCCMS navigates to 'Chi tiết báo cáo' screen 3. Status of report will be change to 'Đang điểm danh' | TRUE | FALSE
45 | View dashboard | Users can view dashboard | 1. Login with authorized account 2. Click on 'Thống kê' in navbar 3. Choose course | 1. SCCMS redirects to 'Thống kê khóa tu' screen 2. SCCMS display dashboard with following information: Total number of students Total number of volunteers Total student registrations Total volunteer registrations Total feedback Admission status Volunteer Recruitment Status Roll Call Summary Gender Ratio of Students Gender Ratio of Volunteers Graduation Rate | TRUE | FALSE